## Sheet1
| Task | Predicted | Spent | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Key
Matthew | Basic chunk renderer | 2 | 2 | [8 empty] | Time | bar: Week 1 to Week 2
| Random cave terrain | 1 | 1 | [8 empty] | Slack | bar: Week 3
| Terrain destruction | 1 | bar: Week 3 to Week 4
| Chunk materials/textures | 2 | bar: Week 3 to Week 6
| Multi-chunk handler | 2 | bar: Week 5 to Week 8
Arjun | Define Enemy Concept | 2 | 2 | bar: Week 1 to Week 2
| Design Enemy Mechanics | 2 | bar: Week 3 to Week 4
| Integrate w/ Cave Generation | 1 | bar: Week 5 to Week 8
| Implement AI | 1 | bar: Week 5 to Week 8
| Test combat and hazards | 1 | bar: Week 6 to Week 8
| Add loot and feedback | 1 | bar: Week 5 to Week 8
Connor | Player controller | 1 | 1 | bar: Week 1
| Input system | 1 | 1 | bar: Week 2
| Movement | 2 | bar: Week 3 to Week 4
| Wall climbing | 2 | bar: Week 5 to Week 8
| Inventory and item collection | 1
| Health | 1
Jack | Basic class structure | 3 | 3 | bar: Week 1 to Week 3
| Tools class | 2 | bar: Week 4 to Week 5
| Visual design | 2 | bar: Week 4 to Week 5
| Sound | 1 | bar: Week 6 to Week 8
Luke | UI Design | 4 | 4 | bar: Week 1 to Week 4
| Script development | 2 | bar: Week 5 to Week 6
| Integration w/ game logic | 1 | bar: Week 7
| Settings | 1 | bar: Week 8
Mikayla | Basic Sound System | 2 | 2 | bar: Week 1 to Week 2
| Design Decorators | 3 | 1 | bar: Week 3 to Week 6
| Integrate Items etc. as needed | 2 | bar: Week 6 to Week 7
| Add Sound to UI | 1 | bar: Week 8
Tyler | Nonreusable class | 3 | 3 | bar: Week 1 to Week 3
| Add tool to unity | 1 | bar: Week 4
| Visual design | 2 | bar: Week 5 to Week 6
| Sound | 2 | bar: Week 7 to Week 8